Representation and Analysis of Spatial Resources in Construction Simulation

| Cheng Zhang Department of Building, Civil & Environmental Engineering Concordia University Montreal, Canada | Amin Hammad Concordia Institute for Information Systems Engineering Concordia University Montreal, Canada | Tarek M. Zayed Department of Building, Civil & Environmental Engineering Concordia University Montreal, Canada |
| --- | --- | --- |

ABSTRACT

Space is one of the resources that may cause crucial problems during construction. Simulation has been widely used in construction to allocate resources and improve productivity or mitigate conflicts. However, simulation does not consider space conflicts in construction process. This paper suggests a new method to represent space resources in construction simulation, which enables visual display of the worksite and the states of the occupation of spaces using a cell-based model. Comparison among different simulation models is made to identify different approaches in space representation.

1     INTRODUCTION

Workspace conflicts are serious problems that can delay construction activities, reduce productivity, or cause accidents that threaten the safety of workers (Guo 2002). Mallasi and Dawood (2004) discussed that workspace interference could result in decreasing work productivity by about 40%. Many researches have been done to detect space conflicts during construction (Riley and Sanvido, 1995; Akinci et. al., 2002; Guo, 2002; Heesom et al., 2003; Mallasi and Dawood, 2004). Workspace conflicts have three characteristics that differentiate them from other conflicts: (1) They have temporal aspects, i.e., they occur only during certain periods of time; (2) They exist in different forms that could change with the requirements of construction activities; and (3) They create different types of problems on site, e.g., compromising the safety of workers or reducing the productivity of equipment (Akinci et al. 2002). Due to these specific characteristic of workspace, it is not easy to detect space conflicts using static methods that focus on specific time points.

Simulation has been used in construction for process planning and resource allocation. Early in the research of Halpin, it was mentioned that location or space-type flow units usually constrain the access to certain work processed and thus constrain the movement of other type units (Halpin, 1992). However, in MicroCYCLONE, space is represented as abstract symbols and it is limited to the operation spaces of equipment, excluding other workspaces, such as moving paths. Kamat (2003) proposed detecting conflicts between any pair of mobile or static objects on a construction site based on collision detection methods implemented within visualization tools of discrete event simulators.

Some researches have been done to investigate the space visualization in construction simulation. Zhang et al. (2002) used 2D icons to represent the resources, which can move along the path between activities. However, this research did not clearly represent the spatial relationships between different activities although there are icons moving from one activity to another activity. It is difficult to understand the worksite situation with links between activities only. Zhong et al. (2004) developed the GIS-based Visual Simulation System (GVSS) to offer planning, visualizing, and querying capabilities of complex construction processes. However, workspace conflicts are not discussed in their research.

Space is not clearly represented in the previous researches of simulation, so sometimes it may be ignored and the results of the simulation may not reflect the real situation of the construction site. In addition, space in a simulation model may change depending on the specific activity, such as the workspace of a crane. Space problems need to be studied in a general way that is easy to understand, and a model should be built in a way that the space can be represented explicitly.

2      Cell-based model

In 1948, John Von Neumann and Stephan Ulam defined a modeling formalism, called Cellular Automata (CA), suited to define spatial systems, and allowing the description of cell-based models by using simple rules (Wolfram, 1986). Space is represented by a uniform grid, with each cell containing a few bits of data. At each step, each cell computes its new state from that of its close neighbors.

In the '70s, Bernard Zeigler defines a theory for Discrete-EVents systems Specification (DEVS). It is a formal approach to build models using a hierarchical and modular approach. Also, he defined a cell space model, which consists of an infinite set of geometrically located cells, each cell containing the same computational apparatus as all other cells and connected to other cells in a uniform way. For a cell located at the origin (0,0), the neatest neighbors would be those located at: (0,0) (the cell itself); (0,1) (1,0) (0,-1) (-1,0) –the cells that are at distance 1 away orthogonally and (1,1) (-1,1) (-1,-1) (1,-1) which are at distance 1 away diagonally (Zeigler, 1976). This paradigm allows the developer to build a Model Base, permitting easy reuse of models that have been validated. A real system modeled with this paradigm can be described as several submodels coupled into a hierarchy. Each model can be behavioral (atomic) or structural (coupled), consisting of a time base, inputs, states, outputs and functions to compute the next states and outputs. The basic idea is that each model uses input/output ports in the interface to communicate with other models.

Based on these ideas, Wainer (1998) developed an approach called Timed Cell-DEVS. The proposal of the Cell-DEVS paradigm considers each cell of a CA as a discrete events model, hierarchical and modular. In this way, complex models can be defined, using a continuous time base. It also allows to associate several kinds of delays for each cell, allowing the definition of complex models easily. The cell state changes according to a local function that uses the present cell state and a finite set of nearby cells. Many applications of Cell-DEVS have been developed including surface tension analysis, studies of ecological systems, and a specification language used to define traffic simulations.

Based on Cell representation of the spatial model, we try to investigate the possibility of representing space situation explicitly when simulating construction process. In the next section, limitations of space representation in traditional simulation model are discussed, and the usefulness of cell-based representation is also investigated in a bridge re-decking project. We apply the Cell-DEVS method in this project and try to link the simulation model with the 4D bridge model to show the space representation and space conflict detection during simulation.

3     Limitations of available simulation models and proposed approach

## Case Study: Jacques Cartier Bridge (Montreal)

The deck of this bridge has been replaced in 2001-2002. The new deck is constructed of precast, prestressed and post-tensioned panels made of high performance concrete which were prefabricated in a temporary plant installed near the south end of the bridge. A total of 1680 precast deck panels were installed, including 410 panels for the main span. The case study will focus on the two activities of removing existing deck sections and installing new panels in the main span of the bridge. These two activities were critical for the success of the project from the point of view of spatial and temporal constraints. The existing deck was removed by saw-cutting the deck into sections similar in dimension to the new panels being installed. Each existing deck section was removed and a new panel was lifted from a truck and lowered onto the new bearing assemblies. Old sections were transported to a dumping area near the bridge. New panels were transported from the plant located in the south end of the bridge. Table 1 shows the tasks and their durations. In Figure 1, the worksite layout is shown when the panels are replaced. Two crews work parallel in different part of the bridge, but only one crew is considered in this paper. Different simulation models are built to investigate the space representation.

| Activity | Task ID | Task Description | Task Durations (min) Triangular distribution |
| --- | --- | --- | --- |
| Remove old sections | 4 | Cut old section | 15, 18, 30 |
|  | 9 | Load old section | 12, 15, 20 |
|  | 10 | Travel of truck with old section to dumping area | 5, 7, 8 |
|  | 13 | Dump old section | 4, 5, 7 |
|  | 14 | Empty old-section truck returns to bridge | 4, 5, 7 |
| Install new panels | 19 | Load new panel | 10, 14, 15 |
|  | 20 | Travel of truck with new panel to bridge | 6, 7, 8 |
|  | 22 | Install new panel | 23, 26, 28 |
|  | 24 | New-panel truck returns to plant | 4, 5, 6 |
|  | 25 | Crane repositioning | 15, 18, 20 |

## Simulation Model of the Re-decking Project Using MicroCYCLONE

A MicroCYCLONE model is built to identify the space resources represented. In Figure 2, spaces are represented as abstract symbols. There are two spaces explicitly represented in this model: Saw space and Truck space, which are represented as queues. Other spaces, like the moving path of the truck and waiting areas, are considered as available all the time and not explicitly represented in this model. In addition, workspaces can change from one activity to another and it is the responsibility of the user to identify these spaces in MicroCYCLONE models. Moreover, spatial conflicts are not discussed except by visualizing the results using post processing applications (Kamat, 2001). In fact, our observation is that space resources are always attached to other resources (equipment, materials, etc.) and heavily depend on the site layout. Therefore, our proposed approach is based on defining spatial resources as an inherited attribute of events.

3.3 3D Workspaces Conflict Analysis Mode

A 3D bridge model is created using Java and Java3D (Zhang and Hammad, 2005) to study the workspace conflicts. Workspaces are created using Constructive Solid Geometry (CSG) (Watt 2000), which means that complex workspaces can be created instead of simple boxes. CSG is a solid modeling method that combines simple solid shapes called primitives to build more complex models using Boolean operators, such as union, difference, and intersection. The workspace of the telescopic crane used in the re-decking project of Jacques Cartier Bridge is shown in Figure 3.

Analysis of workspaces conflict can be done at a specific point of time using a common exact collision detection algorithm (Watt 2000), by which exact overlapped part of different workspaces can be identified and directly shown on the bridge model (Figure 4). However, this method takes computational time and is not suitable for detecting conflicts in real time. In other word, it is not based on discrete event simulation and time is considered as static.

As discussed above, space can be divided into cells and every cell is a discrete event model, so it can change state according to its own time delay and external events. A dynamic information exchange can be achieved during simulation period. Conflict detection can be simplified by checking the state of each cell and avoiding an occupied cell being used by other objects. Based on this idea, a Cell-based model is built to investigate the space issues in construction simulation. In Figure 2, the site layout can be approximately divided into several areas according to the geographic locations, including Bridge, Plant, Dumping Area, Waiting Area, etc. Therefore, the space can be extended to represent the whole working area.

## Cell-based Model Using Cell-DEVS

As shown in Figure 5, there are four main areas in the model: Bridge, Plant, Dumping Area and Waiting Area for trucks transporting old sections, which are represented as separate cell models. To calculate productivity, a Counter is also created in cells. Arrows show the input and output signals between different cell models. Each model is divided into cells, which can be occupied by different equipment and materials over time. Different numbers are used to represent different equipment states and the occupation of spaces. Details of the numbering are shown in Figure 6, which is the graphic interface for Cell-DEVS models. A preliminary test of simplified version of Jacques Cartier Bridge re-decking project is done using this tool. The simplified model does not reflect the topology of the places, and only the main span of the bridge is shown in this model. The cell dimensions are supposed to be 3*3 meters. The total length of the main span is about 600 meters, and the width of the bridge is about 20 meters; therefore, the main span of the bridge can be represented as 200*6 cells.

The behavior of the local computing function is defined using a set of rules with the form: VALUE DELAY {CONDITION}. These indicate that when the CONDITION is satisfied, the state of the cell changes to the designated VALUE, and it is DELAYed for the specified time. Each cell may have a number of states i, j, …, n.

Bridge model: Two cranes (2) and one old panel (3) are initialized on the bridge. One empty truck (1) for loading old panel is also initialized at the beginning of the bridge on the right hand side (Figure 5 (a)). It begins to move and reaches to the position of the panel and changes to 4, which means that the truck is loaded with the old panel. At the same time, the panel changes from 3 to 5, which means the space is empty. The truck 4 continuously moves to the left end of the bridge (Figure 5 (b)). The bridge model is linked with Dumping Area, Waiting Area, Plant and Counter.

Plant model: The signal 4 goes to Plant, indicating old panel has already been cut, and a truck for new panel (9) is generated at the plant and move to the location of the small crane (6), where it changes to 8, which means that the truck is loaded with a new panel. It goes to the bridge and stops at the location of the empty space 5 (Figure 5 (c)). The space will change to 6, representing a new panel being installed (not shown in Figure 5), and after that the cranes move to the left and the next old panel (3) appears in the corresponding position. At the same time, the truck 8 changes to 9, which means it is empty (Figure 5 (d)). The signal 9 goes to Waiting Area model. If there is a waiting truck 2 there, it is activated and changes to 1 then continuously moves to the bridge and begins a new cycle.

Dumping Area: In Dumping Area, the truck 4 continuously moves to the forklift (7) and unloads the old panel, then changes to 1 then moves to Waiting Area.

Waiting Area: In Waiting Area, when it receives signal 1, which means one truck has unloaded the old panel and is ready to go to the bridge for loading another old panel. So the truck 1 changes to 2 and keeps in 2, waiting for a signal from the bridge (9), which indicates that the new panel is installed.

Counter: For the Counter model, when the signal 4 comes, the counter of the old panels will add 1 to the current number. The counter of new panels is also increased when the signal 9 comes.

More complex models can be built by adding spatial constraints, such as adding emergency path on the bridge, or adding another crew on the other side of the bridge. It is possible to simulate the real situation of the construction process using cell spaces. However, linking the cell space to a 3D environment we mentioned in the previous section is our main focus. The 3D workspace analysis model can be used to facilitate analysis spatial issues using cells.

Based on this idea, the whole space is divided into 3D cubic cells with edges of 2 meter length. This level of details is considered suitable taking into account the trade-off between computational time and visualization needs. The cells are divided based on the world coordinate system to get uniformity of the representation. In addition, each cell has a unique ID based on its lower point coordinates. After dividing the space, occupied cells need to be identified. Based on the workspaces generated on the bridge model and using the same collision detection algorithm, the cells that have been occupied at a specific time are identified (Figure 8).

Suitable level of details of time is important both for computational efficiency and for the getting useful simulation results. Large time scale, such as weeks, or days are too long to visually analyze spatial conflicts related to the movement of equipment (Akinci et al., 2003). In cell-based models, different delay times can be associated with internal and external delay functions, space occupation can be detected based on states changing with time.

4     Conclusion and Future Work

This paper tried to analyze spatial issues in construction site using simulation. Different simulation models are built to investigate space representations and conflicts during construction. Dividing space into cells can be used as a general way to represent workspaces and facilitate a simple method to analyze workspace conflicts.

More study has to been done to investigate the possibility of this method. Further link between cell-based model and conflict detection in 3D environment needs more detailed discussion.

Acknowledgments

We would like to thank Dr. Gabriel A. Wainer from Carleton University for his kind help in providing the Cell-DEVS package and supporting us in the development of our application.

REFERENCES

AbouRizk, S., and Mather, K. (2000). “Simplifying Simulation Modeling through Integration with 3D CAD”, Journal of Construction Engineering and Management, 126(6), 475-483.

Akinci, B., Fischer, M., Levitt R., and Carlson, R. (2002). “Formalization and Automation of Time-Space Conflict Analysis.” Journal of Computing in Civil Engineering, 16(2), 124-134.

Akinci, B., Tantisevi, K., and Ergen, E. (2003). “Assessment of the Capabilities of a Commercial 4D CAD System to Visualize Equipment Space Requirements on Construction Sites.” Proceeding of Construction Research Congress, 2003.

Cell-DEVS http://www.sce.carleton.ca/faculty/wainer/celldevs

Davidson, A. and Wainer, G. "Specifying truck movement in traffic models using Cell-DEVS". Proceedings of the 33rd Annual Conference on Computer Simulation. Washington, D.C. U.S.A. 2000.

Guo, S. (2002). “Identification and Resolution of Workspace Conflicts in Building Construction.” Journal of Construction Engineering and Management, 128(4), 287-295.

Halpin, D. W., and Riggs, L. S. (1992). “Planning and analysis of construction operations”. Wiley Interscience, New York.

Kamat, V. R. (2001). “Visualizing Simulated Construction Operations in 3D”, Journal of Computing in Civil Engineering, 15(4), 329-337.

Kamat, V. R. (2003). “VITASCOPE – Extensible and Scalable 3D Visualization of Simulated Construction Operations”, Dissertation submitted to the Faculty of the Virginia Polytechnic Institute and State University in partial fulfillment of the requirements of the Ph.D. in Civil Engineering, Blacksburg, Virginia.

Mallasi, Z., and Dawood, N. (2004). “Workspace Competition: assignment, and quantification utilizing 4D Visualization Tools.” Proc., Conference on Construction Application of Virtual Reality, ADETTI/ISCTE, Lisbon, 13-22.

Wainer, G. (1998). “Discrete-events cellular models with explicit delays”. Ph.D. Thesis, Université d'Aix-Marseille III. 1998.

Wainer, G. and Giambiasi, N. (2001). Application of the Cell-DEVS Paradigm for Cell Spaces Modelling and Simulation.

Watt, A. (2000). 3D Computer Graphics. 3rd Edition. Addison-Wesley Publishing Company Inc.

Wolfram, S. (1986). “theory and Application of Cellular Automata.” Vol. 1, Advances Series on Complex Systems. World Scientific, Singapore.

Zeigler, B. P. (1976). “Theory of Modelling and Simulation.” Wiley-Interscience Publication.

Zhang, C., and Hammad, A. (2005) “Spatio-Temporal Issues in Infrastructure Lifecycle Management Systems.” In Proceeding of 1st CSCE Specialty Conference on Infrastructure Technologies, Management and Policy.

Zhang, H., Shi, J. J., and Tam, C. M. (2002). Iconic Animation for Activity-based Construction Simulation. Journal of Computing in Civil Engineering, 16(3), 157-164.

Zhong, D., Li, J., Zhu, H., and Song, L. (2004). Geographic Information System-Based Visual Simulation Methodology and Its Application in Concrete Dam Construction Processes. Journal of Construction Engineering and Management, 130(5), 742-750.

AUTHOR BIOGRAPHIES

# Text boxes

Cell spaces

Emergency path

Workspace of truck

Workspace of cranes

Waiting Area

Figure 5: Interaction between models

Counter

Figure 2: MicroCYCLONE Model of Jacques Cartier Bridge Re-decking Project

Bridge Model

1: Empty truck for old sections

2: Cranes

3: Old section

4: Truck loaded with old section

5: Old section cut, empty space

6: New panel installed

8: Truck loaded with new panel

9: Empty truck for new panel

Table 1: Task durations

Figure 8: Occupied cells by different workspaces (top view of the bridge)

Waiting Area

Plant

Dumping Area

Dumping Area

Plant

Bridge

Figure 6: Graphical display of the Cell-DEVS model

Part of Bridge

Moving Truck

Panel

Two cranes

Dumping Area

Waiting Area

Plant

Counters

Bridge

(a)

(b)

(c)

(d)

Figure 7: Part of Bridge Model showing the states of each cell

Small crane

Forklift

Old Panel

Empty space

Empty truck

Truck with old panel

Truck with new panel

Empty truck

Next old Panel

- Workspace of a crane superimposed on a picture of construction site

(b) Generating the composite shape of the crane workspace using CSG

∩

Composite workspace of crane

Workspace for boom

with complete lifting

zone

Workspace for

crane body

Intermediate shape

representing range

of boom horizontal

rotation

Time 1

Time 4

Time 2

Figure 3: Example of workspace of a telescopic crane

Dumping Area Model

1: Empty truck for old sections

4: Truck loaded with old section

7: Forklift

Old Section

Crew-2

Time 3

Old Section

Crew-1

Waiting Area Model

1: Empty truck for old sections

2: Empty truck waiting

Plant Model

6: Small crane

8: Truck loaded with new panel

9: Empty truck for new panel

Truck with new panel

Empty truck

Workspace for boom

with partial lifting zone

Figure 1: Worksite layout of the bridge

Conflict between workspaces

of crane and cross truss

Cross truss element

Conflict between

workspaces of crane

and emergency path

Panel to be replaced

Workspace of straddle crane

Emergency path

Figure 4: Conflict detection in the case of straddle crane