SYSC 4907

Forth Year Engineering Project Proposal

Carleton University Carpool System

Group Members:

Guangjie Joey Deng…100298750

Andrew Lyn………….100299121

Supervisor:

Professor Gabriel Wainer

1. Introduction

This is a proposal for a 4th year engineering project SYSC 4907 entitled “Carleton University Carpool System.” This project is expected to be delivered by April 2005.  The group members are Guangjie Joey Deng (100298750), a 4th year software engineering undergraduate, and Andrew Lyn (100299121), a 4th year computer systems engineering undergraduate. We will proceed with this project under the supervision of Professor Gabriel Wainer.

The project is composed of a project proposal, written progress report, oral presentation, final presentation, poster fair demonstration and final report. The expected date of completion for the project is April 8th, 2005. The project relates to the material learned in the programming courses, software architectural planning, and other courses related to software development. In addition, within this document is the background information of this project, proposal, along with a brief schedule.

2. Objectives

The main objective of the project is to produce a piece of software that could help reduce air pollution and road damage, by providing a cost effective way for students to travel to Carleton University. Our goal is to complete the “Carleton University Carpool System” software and have it setup on a web server to provide service to students and faculty according to our plan.

In this project, our plan is to set up a mail server, html server, and program a carpool system. Andrew and Joey both will be the main software programmers in this project.

3. Motivation

The process of creating professional software is fascinating, it captivates our attention, and hence we choose to do this project. We want to learn the development process of creating professional software, and it gives us the chance to learn how to interface a database with a real-life application. We expect to improve our interpersonal communication skills, throughout the project.  So we are better prepared for the future’s challenge.

4. Background on Car Pools

Air pollution, traffic and road repairing within city are big headaches among city designers. As population increases pollution and traffic increase, therefore a solution to the problem is needed quickly. We want to reduce traffic and clear our air without sacrificing too much.  A car pool system allows people to travel in groups. Having fewer cars on the road is a benefit because it will reduce repairing cost of the road, and decrease the amount of car emissions improving air quality.

5. Proposal

We propose to create a car pool system that connect people who travel between cities, and allows them to share transportations. We will divide up the components required to complete the project with each member responsible to complete the development, integration and testing of their individual components. Joey will complete the development of the database and the general software development, and testing. Andrew will be setting up web server, email server, and research on legal matters regarding privacy and testing.

6. Technical overview

This is a very software oriented project, and therefore we will apply everything we have learned from these past four years to complete this project. First of all we will make a schedule and plan each individual’s duty on this project.

Then we will start working on this project:

- review the work done by the team from last year, then we will pick up from where they left off;

- gather requirement of project;

- analysis and design the system;

- set up the database server;

- set up the mail server;

- research on privacy issue;

- implement the design on software by using Java;

- after main elements are done, we will integrate them together so they will function as a whole system; and

- when the system is done, it will be time to test it.

7. Schedule:

| Activity ID | Task_Name | Duration | Start_Date | Finish_Date |  | Resource_Names |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | write proposal | 5 days? | 9/12/2004 8:00 | 9/16/2004 17:00 |  | Joey Deng,Andrew Lyn |
| 2 | submit proposal 1 | 1 day? | 9/17/2004 8:00 | 9/17/2004 17:00 |  | Joey Deng |
| 3 | rewrite proposal | 6 days? | 9/18/2004 8:00 | 9/23/2004 17:00 |  | Joey Deng,Andrew Lyn |
| 4 | submit proposal 2 | 1 day? | 9/24/2004 8:00 | 9/24/2004 17:00 |  | Joey Deng |
| 5 | review previous work, gather requirement | 7 days? | 9/25/2004 8:00 | 10/1/2004 17:00 |  | Joey Deng,Andrew Lyn |
| 6 | set up softare in the lab | 7 days? | 9/25/2004 8:00 | 10/1/2004 17:00 |  | Joey Deng |
| 7 | set up database | 7 days? | 9/25/2004 8:00 | 10/1/2004 17:00 |  | Andrew Lyn |
| 8 | set up mail server | 7 days? | 9/25/2004 8:00 | 10/1/2004 17:00 |  | Andrew Lyn |
| 9 | design the system | 5 days? | 9/27/2004 8:00 | 10/1/2004 17:00 |  | Joey Deng,Andrew Lyn |
| 10 | implement the software | 151 days? | 10/2/2004 8:00 | 3/1/2005 17:00 |  | Joey Deng |
| 11 | research on privacy | 5 days? | 10/4/2004 8:00 | 10/8/2004 17:00 |  | Andrew Lyn |
| 12 | varify, validate softare | 114.5 days? | 11/7/2004 13:00 | 3/1/2005 17:00 |  | Andrew Lyn |
| 13 | write progress report | 7 days? | 11/29/2004 8:00 | 12/5/2004 17:00 |  | Joey Deng,Andrew Lyn |
| 14 | submit progress report | 1 day? | 12/6/2004 8:00 | 12/6/2004 17:00 |  | Joey Deng |
| 15 | last change for oral presentation | 3 days? | 1/5/2005 8:00 | 1/7/2005 17:00 |  | Joey Deng |
| 16 | prepare for presentation | 9 days? | 1/4/2005 8:00 | 1/12/2005 17:00 |  | Joey Deng,Andrew Lyn |
| 17 | oral presentation | 3.33 days? | 1/17/2005 8:00 | 1/20/2005 10:40 |  | Joey Deng,Andrew Lyn |
| 18 | last change to poster fair | 5 days? | 2/7/2005 8:00 | 2/11/2005 17:00 |  | Joey Deng |
| 19 | prepare for poster fair | 17 days? | 3/1/2005 8:00 | 3/17/2005 17:00 |  | Joey Deng,Andrew Lyn |
| 20 | poster Fair | 0.5 days? | 3/18/2005 8:00 | 3/18/2005 12:00 |  | Joey Deng,Andrew Lyn |
| 21 | write final report | 19 days? | 3/6/2005 8:00 | 3/24/2005 17:00 |  | Joey Deng,Andrew Lyn |
| 22 | submit final report 1 | 1 day? | 3/25/2005 8:00 | 3/25/2005 17:00 |  | Joey Deng |
| 23 | rewrite final report | 15 days? | 3/24/2005 8:00 | 4/7/2005 17:00 |  | Joey Deng,Andrew Lyn |
| 24 | submit final report | 1 day? | 4/8/2005 8:00 | 4/8/2005 17:00 |  | Joey Deng |

8. Conclusion

Our goal is to learn the development process of professional software through undertaking this challenging project (“Car Pool System”). Furthermore, it is hoped that this information will help students to know more about this technology and its potential to reduce air pollution and traffics. In addition, we will show case the advantage of using this technology. If you have any questions or concerns about this project, please contact Joey and Andrew at joeydeng@hotmail.com.